## Slide 1
Lostock Sustainable Energy Plant (SEP)
Local Liaison Committee
29th November 2018

## Slide 2
AGENDA
      Welcome & Introductions
      Proposed Power Upgrade Application
      Update on Site Works Since Last Meeting
      Proposed Work Activities in Next 3 to 6 Months
      Subsequent Project Works
      Date of Next Meeting
      AOB

## Slide 3
Welcome & Lostock Site Rules
  Welcome to the seventh Lostock SEP Local Liaison Committee
  Office Rules
    TATA representative will act as Guardian
    No fire alarm test planned for today. If alarm sounds follow Guardian to muster point in staff car park at the rear of the building
    Toilet facilities on this floor
    Smoking Prohibited in the office.

## Slide 4
Project Overview
Lostock Site History and Overview
  Lostock Site commenced soda ash production in 1907; Brunner Mond (now TATA Chemicals Europe Ltd) acquired the site in 1904. Demolished and rebuilt new manufacturing plant.
  Soda ash produced from brine (NaCl) and carbon dioxide (CO2)
    Brine supplied from the Holford salt cavities operated by Inovyn
    Carbon dioxide produced from the thermal decomposition of limestone with coke. Limestone railed in from Buxton
    Ammonia is used as a catalyst (pH conditioner) to assist the chemical reaction
  Soda Ash production is energy (heat) intensive. Steam required to drive the chemical reactions and dry the product.
  The site operated its own coal fired power station (six boilers) up to the year 2000. Decommissioned when new gas fired CHP power plant started at Winnington

## Slide 5
Lostock Site Aerial

## Slide 6
Lostock SEP: Project Overview

## Slide 7
Lostock SEP Project
  Power Upgrade Variation Application

## Slide 8
Power Upgrade Variation Application
Background
As previously reported, technical studies conclude that the electrical power output the plant could deliver to the national grid could be increased.
Proposal developed for an electrical power increase of up to a further 30 MWe
  This increase is delivered :
    Without change in any of the parameters permitted under the existing consent granted by the Secretary of State on 2nd October 2012 for construction and operation of a EFW station generating up to 60 MWe
    Enabled by efficiency improvements since consent was granted.
Special Local Liaison Committee meeting held on 15th March with Chris LeCointe, RPS, in attendance
    Information leaflet and CD provided to allow local information sharing and opportunity to ask questions.

## Slide 9
Power Upgrade Variation Application
Progress Update
A Variation Application was formally submitted to DBEIS seeking to vary the 2012 Consent to increase the power output of the Plant from the currently consented 60 MW to up to 90 MW.
DBEIS provided notice to TATA under Regulation 4(6) of the Variation Regulations that it considers the Variation Application to be suitable for publication.
TATA consequently published notice in accordance with Regulation 5(3) & (5) of the Variation Regulations on Thursday 2nd and 9th August 2018.
    Application documents made available for inspection:
      On SEP website: www.lostockpower.co.uk
      At Northwich Library and at CWACC, Wyvern House, Winsford
Representations on the Variation Application were invited until 7th September 2018. Statutory consultation concluded on 4th October

## Slide 10
Power Upgrade Variation Application
Progress Update (2)
Statutory Consultees included: Cheshire West and Chester Council and the Environment Agency
TATA has, via RPS responded to DBEIS on the points raised in the representations received.
The redacted representations and TATA’s response are now uploaded to the SEP website: lostockpower.co.uk .
DBEIS will consider the Variation Application and representations received and may consent to vary the 2012 Consent or may refuse to vary the consent.

## Slide 11
Power Upgrade Variation Application
Progress Update (2)
Three main themes within the representations received for the variation application:
  Fuel type
  HGV Movements
  Air Quality Impact
Fuel Type – Pre-treated waste and C&I was as dictated within Condition 31 and Condition 32.
HGV movements – as Condition 9 within the Planning Consent
BEIS assessed that the impact of the proposed variation and determined that no EIA was required as it was unlikely to have a significant impact.

## Slide 12
Lostock SEP Project
  Update on Site Works Since Last Meeting

## Slide 13
Work Activities Since Last Meeting
Asbestos Removal
Specialist contractor working on site removing asbestos within the two main redundant power station buildings.
Expect to complete site works Quarter 1 of 2019.
Site Surveys
GPR survey of the entire site
Drain service CCTV survey
Bird netting of the power station buildings
Detailed Design of Enabling Work activities
Detailed design of the new water treatment plant and electrical sub-station being progressed. Aim to build and commission next year
Design specification for tie-ins. Aim to be completed in new year

## Slide 14
Lostock SEP Project
Proposed Work Activities Over Next 3 to 6 Months

## Slide 15
Work Activities in Next 3 to 6 Months
Installation of temporary workshops, amenities, offices and laboratory
  Ground preparation for temporary facilities
  Provision of required services
  Demolish existing structures to make land areas available for the commencement of construction activities
Commence civil works for the new water purification plant and the new electrical sub-station
Complete identified tie-ins to allow water treatment plant to be commissioned
Commence demolition of sections of the redundant power station buildings
Submit planning applications for new Office block and workshops
Prepare areas for the construction of the new office block and workshops.
Environmental Permitting
  Conclude with Environment Agency the TATA and LSEP permit boundaries

## Slide 16
Lostock SEP Project
Subsequent Project Works

## Slide 17
Lostock SEP: Subsequent Project Works
Efforts during early 2019 will largely focus on:
  Commence demolition of the old coal fired power station buildings
  Relocation of services to allow construction works to commence later in the year.

## Slide 18
Lostock SEP: Date of Next Meeting
  Proposed Dates for Future Meetings:
  Thursday 28th February 2019
  Thursday 23rd May 2019
  Thursday 12th September 2019
  Thursday 28th November 2019

## Slide 19
Lostock SEP Project
AOB